## Projects Summary
S.No. | TASKS | Type | Requestor | Status | ETA | Owner | Comments
1 | Ladbrokes SIA changes | Roadmap | BI | DONE |  | Sudhakar
2 | SSL for rundeck | NFR |  | DONE
| Kubernates Autoscalling with KEDA |  |  | POC DONE |  |  | Its done on Kubernates Minikube Env
3 | CDNA new requirements changes | Roadmap | Ivana | DONE |  | Sudhakar
4 | AATM Mongo | NFR |  | DONE |  | Sudhakar
5 | Hadoop | Roadmap | BI | IN PROGRESS |  | Sudhakar
| YARN High availabilty |  |  | DONE
| HDFS High availabilty |  |  | DONE
| YARN Multi tenancy |  |  | DONE
| Hive |  |  | DONE
| Hive on yarn |  |  | DONE
| Hive+Spark+Yarn |  |  | DONE
| H2o.AI |  |  | DONE
| Hadoop cluster migration |  |  | DONE
| Hadoop Resource scaling |  |  | IN PROGRESS |  |  | CHG125256 need to implemet this CR Pending with INFRA
6 | Prometheus/AlertManager Rollout plan | NFR |  | IN PROGRESS |  | Sudhakar
| Kafka,mongo,node,elk exporters |  |  | DONE
| Kafka Exporter |  |  | DONE
| Kafka Lag Exporter |  |  | DONE
| Monitoring US ELK kafka with Prometheus |  |  | DONE
| Prometheus Yarn monitoring |  |  | Yet to Start
| Prometheus Spark monitoring |  |  | Yet to Start
7 | KAFKA and JAVA Upgrade | NFR |  | IN PROGRESS |  | Sudhakar
| Java Upgrade |  |  | Yet to Start
| Analytics kafka expansion HA |  |  | Yet to Start
| Upgrade Analytics kafka 2.4 kafka version |  |  | Yet to Start
| Zookeeper upgrade of Analytics kafka |  |  | Yet to Start
| pg-switchboard compatibility |  |  | Yet to Start
| String messages compatibility |  |  | Yet to Start
| cross kafka cluster compatibility |  |  | Yet to Start
| Analytics Kafka Hostname changes |  |  | DONE
| Analytics Kafka expansion |  |  | Yet to Start
| CMAK |  |  | DONE
8 | Redis | NFR |  | IN PROGRESS |  |  | Production rollout is pending
| Redis-commandar |  |  | DONE
9 | US datapoints migration | Roadmap | BI | IN PROGRESS | 24th May | Sudhakar/Durga
| Analytics ESB |  | BI | IN PROGRESS |  | Sudhakar/Durga | Need to raise nodes
10 | CRM Realtime Dashboard | Roadmap | CRM | IN PROGRESS |  | Sudhakar
| Wallet dashboad changes |  |  | On HOLD |  |  | Waiting on source
| Bonus Changes |  |  | DONE
| Login Changes |  |  | DONE
| Bingo ticket |  |  | DONE
| Golden Coin |  |  | DONE
| Freespins |  |  | DONE
| Kibana User Access |  |  | DONE
| Unique dashboards - Entain labels, US and LCG |  |  | IN PROGRESS | 26th May
11 | Performance Improvements | NFR |  | IN PROGRESS
| Scale JsonFilter & Performance impovement |  |  | DONE |  | Sudhakar
| Scale Transaction services & Performance impovement |  |  | DONE | 20th April | Sudhakar
| TEP code refactoring |  |  | DONE |  | Mohith
| JFS code refactoring |  |  | DONE |  | Mohith
| NIFI scaling |  |  | DONE |  | Durga
| Hadoop cluster Performance improvement |  |  | IN PROGRESS | 19th July | Sudhakar | Post production freeze
| Graphyte Performance issues |  |  | DONE |  | Sudhakar
| SPP consumer lag issue |  |  | DONE |  | Sudhakar | Monitoring the service
| ARC project events performance issues |  |  | DONE |  | Sudhakar
| ADA bhehaviour events performance issues |  |  | DONE |  | Sudhakar | Monitoring the service
12 | Apache bookeeper | NFR |  | Yet to Start
13 | Environment Requirement Cashier: deposits, cashout requests, payments. Poker gameplay: Hands played, winnings, gametype, etc.. Teradata player tables. | Ops item | Vincent Castelain | Yet to Start |  |  | Needs clarity on requirements
14 | Opensource JBPM (setup and HA) | NFR |  | Yet to Start
15 | Bonus Abuser | Roadmap | Barry | Yet to Start | 25th June
16 | Apache Druid | NFR |  | Yet to Start |  | Mohith
17 | Phone encription for snapchat integration | Roadmap |  | Yet to Start |  | Sudhakar
18 | Openshif issues support | NFR |  | On HOLD |  |  | Rajeshwar to confirm
19 | Cloudflare Integration | NFR | PEG | On HOLD |  |  | Waiting of PEG to provide go ahead
20 | CASIA-CASINO data routing | Roadmap | Casino | On HOLD |  |  | Pending with ADA team (Andras)
21 | Bingo purchase events consumption | Roadmap | Bingo | IN PROGRESS | 26/05/2021 | Mohit | Prod deployment pending
22 | Scout testing & Production deployment | Roadmap | Compliance (Jeff) | On HOLD |  | Sudhakar/Durga | Waiting on Jeff. Jagan to communicate freeze period
23 | ARC project events | Roadmap | BI | IN PROGRESS | 26/05/2021 | Sudhakar | Cashier events are pending